Minutes: Meeting 6pm, Friday 2nd August 2024.

Present: Julian, Chris, Claire, Kim

Apologies: Mike

- Minutes of the previous meeting - agreed

- Matters Arising.

Action Points.

Funding Application for Locality Funding JC to liaise with CCR and submit application. - done.  Money received.

Other action points to be discussed in today’s meeting.

- Housing Survey.

Further discussion about what may be included in any Survey questions and landowner involvement. —CCR and JRC

Changes to NPPF/ govt approach to housing

We can ask

Type of housing people would prefer?

Within the village or

Number of housing people would prefer?

Location - need to understand if any landowners want to put forward (‘call for sites’ type idea)

CIL considerations

Any housing survey needs to come after the GI survey - findings

Need a large section on housing and need to see over the next few months what happens with national legislation.

- Business Survey

Simon Bath - reply received and circulated.

Kim’s received

DIY Solutions received

Roxton Garden Centre - no reply as yet

GAP housing? Are they staying? Relocating?

Church - MP has had discussions with St Mary’s main concern is lack of burial space. Would like to contribute to draft plan.

Chapel - would like a paper copy of BS.

Sheds, Happy Brewer…

All to keep circulating.

- GI Survey - comments from all on structure of the survey.  First public meeting now October due to OS information needed to be obtained along with BRMC mapping.

- OS licence app - RPC Clerk to apply for license.

Hall booked 17th and 24th October - ideally 24th. 6.30ish onwards/ 7pm?

- Need large turnout. 30-35 people is 15% so that’s a good minimum.

- Thursdays

- Will open the bar, raffle, invite the fish n’ chip van?

- Update from RPC

- MOT appeal- update from CE - hearing postponed (October?)

- Mulberry Homes meeting - parking spaces, sign, Section 278 discussed and RPC will be working with Mulberry Homes for them to come up with a suitable proposal regarding traffic management changes.

- Bins

- For RPC to do:

Noise Barrier A428 has been reduced - ask NHighways to come and speak to RPC.

School Lane/ A1 site.

Follow up with Mulberry Homes.

NPSG would like to tell RPC about GI study and dates.

- Roxton Flower Show -  stall at the meeting to update people on our progress?

- AOB.

- Next meeting: Friday 13th September 6pm - 42 High Street