Neighbourhood Plan Steering Group 		Meeting 26th January 2024.

Present: Julian, Claire, Mike, Kim, Chris

Apologies: Sue, Brian

Minutes:

- Minutes of the previous meeting - approved

- Matters arising from the previous meeting:

Action points.

- Improvements to the website to make it fit for purpose - done

Each month, try and improve the website (1 hour a month)

- Photo credits

- Any other comments to Claire over the next few days

  - Claire then to email minutes of this meeting (#5) to upload

Consultations in November -  verbatim comments have been uploaded to the website

- Short summaries from each area following the November Village Consultation Meetings.

Claire has drafted the leaflet - 6 pages at the mo

Kim to suggest edits - get down to 4 pages (1 sheet of A4) on Monday

Claire to send to printers by 31st Jan

All to leaflet drop (maybe next weekend?)

- Website update and any further improvements required. - Roxtonplan.org.uk

See above - covered under 2.

- Next stage in our consultation with the Village:

Play back November responses via website and leaflet drop.

Further interaction with the community via public meetings and questionnaire - what will be the order?

Step 1 - Speak to landowners

Step 2 - Consulting with other stakeholders - landowners, businesses, Bedford Council, NGOs, etc.

Landowners

Julian and Mike - Simon

Claire - Janet (+ family)

Claire / Chris - speak to Justin about then speaking to Highways England (about CPO land)

Julian - Garden Centre, Roxton Lock Cottage land/ lakes

Other land owners - find out and contact - Claire to ask Justin

Businesses

Claire to draft a questionnaire to send out to local businesses.

ALL to speak to local businesses as much as possible to engage (in addition to the Q).

- Kim - Ford Lane businesses, Park Lane

- Cafe

- Post Office

- Royal Oak

- Claire - High Street - Janet and Howard

TJC, Counselling business on Saxon Close

- Garden Centre

- Black Cat Farm Shop

- Happy Brewer

- GAP windows

- Merit Garden Products ltd. Shed company

- Scaffolding - Chris

Other local businesses (not necessarily economic)

School - Hayley

Church - Julian and Mike to speak to the vicar

Chapel - Chris

Other NGOs/ GOs-

Bedford Borough Council - highways, planning, conservation officer

BRCC

Env Agency, Canals and Rivers Trust, CPRE

Historic England, Natural England

Local History Group

Claire/ Julian to draft a letter for these - Julian has seen one as an idea

Utillities and developers

- Anglian Water, National Grid, BT

- Mulberry Homes

Larger companies/ stakeholders

- Highways England

- EWRail

Some discussion about involvement/ introduction from RPC for larger/ national stakeholders

Surrounding parishes and parish councils

- Tempsford, Great Barford, Wyboston

Draft letter - Claire and Julian to draft

Step 3 - Drafting questionnaire - by end of March

Divided up responsibility for these interactions and timing.

- Green Infrastructure Survey

Julian needs to speak to Jemma (BRCC) and others about what this involves. Other NP Groups, Natural England, BRMC (consultancy), etc.?

A GI survey highlights areas for possible development, amenities in the area, etc.

Professional consultation needed. Further funding needed for this?

- AOB

- What might be the role of local media? Radio, newspapers (but also social media)

- Looking forward to next grant - what will we need for next financial year

- Claire to send Robbie these minutes to upload!

Next meeting: Friday 1st March 2024 @ 15 Ford Lane