15th December 2023

Present: Julia, Chris, Mike, Kim, (Claire on Facetime)

Apologies: Sue

- Minutes of the previous meeting.

- Matters arising from the minutes

- Locality funding - we have!

- Phase 1 Consultation event held at village hall

- Other than that - no matters outstanding

- A review of the Consultation Meetings on 17th and 19th November.

Major issues raised. Timing in playing these back to the community. Lessons learnt from the meetings.

- Comments have been written up from the events on 17th and 19th: link here

- Any further comments to be received by date? how sent to us?

info@RoxtonPlan.org.uk

- Next RPC meeting on 8th Jan 2024

- Suggested that any further comments given by 31st January?

- How to get comments out - leaflet drop again?

- Create a Wordcloud?

- Create a leaflet

Surveys then created and sent out after this

(Bedford Local Plan 2040 has been rejected - and it’s to be adjusted. Implications for when the survey can be sent out)

Learning:

- Good to coincide with event at the school - a few people called in afterwards

- Good to coincide with the bar being open

- Few more posters outside to encourage people in - passing trade

- Ensure posters are up earlier (in PO, VH bar, etc.)

Update on website - Following further discussions with Robbie Bayes.

Claire to email Robbie this weekend

Introduction on home page to N Plans and the process

Change cover photo ASAP and add images - send new photos as an attachment. Images so important!

Latest news - no news to report! - change! - link to comments doc. Use this for explaining what stage we are at/ what we are doing now/ next. Linked to a banner headline idea.

Check minutes

Timeline - edited

Who does the email go to? Where does it go - Claire and Julian’s emails. They can then put it on the shared drive.

Email address needs to be hyperlinked.

Ask for a timeline - how quickly can the website be up and running? One more check once done.

Email SG his response.

Revisiting our aims for Q1 24.

- Next steps - get responses back, leaflet drop, survey

- How will we approach local businesses, farming community, etc.?

- Julian and Mike to go see Simon Bath

- Julian  to speak to Manager/ owner of Garden Centre

- Talk to Janet/ Janet’s nephew

- Bates

- Claire to speak to Justin

- Reminder - a lot of the land has been CPOd by Highways England/ National Highways - so need to speak to them.

- Claire to speak to the headmistress/ governors of the school - Hayley Mudge (co-chair of Board of Governors)

- Mulberry homes

- Roxton Lock Cottage

- Fishing Syndicate

- Any other businesses/landowners?

Finance/cost procedures

- Money we have from Locality - only sums above £1000 need to be played back to them. Anything below that signed off by Diane.

- We need to refer to Julian/ Claire to keep track of expenses.

- Keeping a spreadsheet of finances/ costs - Diane to cross ref.

- Claire to share the finance spreadsheet with Diane too.

Enquiries via RPC

- No further enquiries

AOB

- None

- Next meeting: tbc