Present: Claire, Kim, Julian, Chris

Apologies: Mike, Sue, Brian

Minutes of the previous meeting - approved

Matters arising - key action points - most have been dealt with

Website update.

Domain name - Roxton plan.?

RoxtonPlan.org.uk 	£11.99 per year

Julian to move ahead on this

Email etiquette

- Need to establish an etiquette for replies - auto-reply to explain to anyone emailing

- Anything straightforward can be responded to

- Have the one email address? info@roxtonplan.org.uk - everyone on the steering group will get access to it.

- FAQs can probably be quicker

Locality Funding application

£1845 applied for - to cover website, etc.

In the system and turnaround should be moderately quick - Diane said roughly 2 weeks on one occasion, so we’ll see.

Julian to let Diane know that we’ve applied

Communication Strategy -

Leaflet.- sign off

- unbusy the leaflet - too many pages - need to simplify

- Kim to help Claire to simplify the language, etc. - sent to the printers by the end of next week (27th)

- Claire to create a poster to display in a few places.

Distribution of the leaflets - will split

Meeting on 6th November at 6pm - Mayor’s meeting - can hand leaflets out/promote the launch event then as well.

Photos

- Oliver Nicholson Clinch to take 20-25 photos to use on the website, etc.

Village Hall Meetings 17th and 19th November

- Village hall is booked

- Will we have a website by then? Can connect a laptop to the TV.

- Assigning responsibilities…

- The Neighbourhood Plan Process - general ‘stall’ for information - Julian

- Housing - Kim

- Environment and Green Infrastructure (including rural character) Mike

- Employment - Sue?

- Getting About and Transport (within and external to the village)/ Infrastructure - Chris, then Julian on Sunday

- Heritage and the historic environment - Claire

- Amenities and Facilities - Brian?

Around the hall, there can also be (large) copies of existing ‘paperwork’/displays for people to read/reference:

- A map of the area covered by the NP

- Map of the conservation area

- Copy of the Conservation Designation document

- A (more detailed and contextualised) map of EWR’s proposals

- Maybe a board with our pics on so people know who the Steering Group is?

- Copies of the Local Plan 2030 and proposed Local Plan 2040 (showing specifically where the industrial warehouses are planned in relation to Amended route 1 EWR and Roxton village)

- Copies of the two/three major planning proposals from the past few years - School Lane, Parcels A&B, HGV Lorry Park

Claire will create a folder in the shared drive called “DISPLAYS’ - if you want anything printing - put in there with name to say size and copies e.g. ‘Map of the Conservation Area, A1, x1’ by 8th November so Claire can send to the printer. A1 as default?

Flipchart

Collecting feedback

Requirements for the meetings.

AOB

- Next meeting: 1st December 2023 to discuss responses to the launch event

(Chris apologies in advance)

- We will have mulled wine