Present: Julian, Kim, Sue, Chris, Mike, Claire

- Minutes of the previous meeting

Previous minutes accepted

- Green Infrastructure Survey - BRCC meeting update

BRCC - Julian fed back from the BRCC meetingabout Green Infrastructure. Kim also fed back.

Should get another qute for due diligence.

Housing allocation? Further funding would be available - this is something we can include on the questionnaire (and NP)

- Matters arising/ update on actions from previous meeting

- Contacting local landowners and businesses - ongoing

Everyone to continue speaking to local landowners - see previous minutes

- Draw up a business questionnaire template

- Claire to draft a business questionnaire and send round to NPSG, and then local businesses

- Importance of wifi (fibre)

- Contacting other NGOs and organisations - on going

Everyone to continue speaking to other orgs - see previous minutes

- Distribute leaflets to village updating on November consultation and get feedback-leaflets distributed

- Claire to chase for an invoice from Lion Press!

- Feedback on social media talking about the feedback leaflet was positive

- Claire to add any further comments received as part of Stage 1 consultation to the transcribed document

- Contact BRCC to arrange meeting on Green infrastructure- done

- Kim to find second or third quote for a GI survey/ plan

- Begin drawing up survey questions- on going

- Discussion about what to do when (business survey, landowner consultation)

- Other NPs did 2 surveys - initial survey and then a second one after consultation with businesses/ landowners

- Would be interested to hear from the school before constructing the survey (as affects a lot of aspects of the NP)

- Survey - timing - survey monkey to be paid for in March 2024 - a year’s license (£400).

- WIll need beta testing

- Will need unique references so people don;t complete a paper copy AND an online copy

- Further Public Meetings

Other NPSGs have had regular public meetings. Do we want another? May 2024? Before the survey!

Presentation and Q&A this time.

Also need to bear in mind the BRCC GI workshop. Combine? After the general presentation and Q&A.

To be discussed next meeting - after we’ve decided on GI

Everyone to start thinking about stakeholders and local interest groups - to encourage attendence/ numbers at the public meeting

- Budget 24/25

- 1st/ 2nd week of April - new budget finalised

- Separate application for housing?

- Everyone to start thinking about what we need money for next year

- AOB

- Julian to update Jemma at BRCC in general

- Recent planning apps - NPSG are wondering why the developer (Rainer) did not think to engage with the NPSG?