05.04.2024 Minutes

- Minutes of the previous meeting.

Matters arising and Action Points:

- Contacting local landowners, NGOs and other organisations - ongoing, update.

  - Simon (and his PA) - Julian will meet

  - Business Questionnaire ready to give to him

- Business questionnaire to be distributed.

- Claire to email the final draft

- for any comments from other NPSG members - by next week Sunday, so we can get it out.

- Chase invoices for the current budget year. 23/24. Julian and Claire - Done.

- Diane is returning unspent funding - £259 underspend.

- Obtain a second Green Infrastructure quote - update.

- Kim chased 2 other firms but they haven’t come back. On this basis, assume they have no interest.

- Julian to ask another NP group who they used.

- Contact Jemma at BRCC to update on our progress and talk about possible Housing Survey. Julian - contacted. Update given. Will be added to next agenda for discussion.

- Purchase Survey Monkey -software package.- Done.

- Rainer Development Planning application - update.

Implications for Neighbourhood Plan.

Will wait until after the extraordinary RPC meeting.

Reply and suggest some dates to meet - 11th or 12th onwards. Evening better. Ideally, meeting with the landowner, Rainer and Marrons. We need to discuss what happens in both possible scenarios - if the planning app is approved or rejected (decision still pending).

- Budget 23/24.

Closing Balance. Diane to finalise.

Funding application for 24/25 -items to include:

- GI survey

- (Housing need survey? Quote received. 20-35% return rate. Social housing - importance of access to local residents looking to remain in the village

Everyone to put forward their questions. Email Julian questions by next meeting.)

- Printing costs

- Public events

- Village Hall hire

- Heritage/ History Tour

- Accessibility review? Depends on cost.

Everyone sends rough costs by the next meeting

Apply for 2024-25 funding from Locality! Aim to get the grant application in by early May.

- Survey and Public Meeting - possible dates

1 or 2 surveys, with a first round and a second round, with the second after feedback?

What do we need to know?

GI workshop before the GI survey.

Gi business before the other survey.

Meetings - Calendar for 2024-25, including events - Julian and Claier to draft for others to add to.

- AOB. None

- Date of next meeting: 3rd May 2024 - 6pm or 7pm