13/09/2024 NPSG Meeting Notes

Attendees:

Julian Chillingworth

Kim Gubler

Mike Peebles

Chris Evans

Apologies:

Sue Holland

Claire Camilleri-Rose

Brian Vaughan

JC opened the meeting.

Apologies for absence noted

The minutes of 02/08/2024 were accepted by those present.

JC noted matters Arising would be covered by the Agenda:

Housing Survey:

RPC has been canvassed to sponsor a survey by BRCC. NPSG has no budget to proceed with this

Business Survey: 
Simon Bath reply received and circulated, no further responses have been received and it was noted this is in line with the experience of Renhold NPSG

GI Survey:

JC noted this has been more problematic than anticipated and there is more pre work required:

- OS licence – necessary for Beds RMRC to draw up the maps necessary to start the GI Survey. This has to be applied for by RPC and not the NPSG. No problem foreseen as there is no cost involved – actioned, signed by Chair RPC, with JC for submission @ 08/10/202

Due to the delay in starting the date for the first public meeting/workshop needs to be moved from 17/10/24 – actioned by JC first date moved to 21/11/2024.

Church and Chapel:

The NPSG noted MP has had discussions with St Mary’s main concerns lack of burial space and the desire to to contribute to draft NP.

MOT appeal:
CE updated the NPSG. RPC has appointed a Kings Counsel to represent the village against this planning application appeal at a cost of £4,000. It has been postponed more than once and is currently due to be heard on 23/10/2024.

Rainer Development:
This application is in train and the NPSG decided to engage and influence if circumstances allow for the benefit of the village

Website revamp:
It was noted the website needed to be updated with current documents and needs a general tidy up. Action all: look at website to ID any potential improvements for the next NPSG meeting.

RPC Update:

No updates

There was no AOB.

Date for the next meeting is 18/10/2024 to be hosted by MP at 4 Southfields.